## Agile Template
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US/101 | Collect real company financial documents (annual and quarterly reports, financial statements, SEC/regulatory filings, earnings reports, investor presentations, MD&A, notes to financial statements) for approx. 5-10 companies, with 2-3 years of annual reports each (suggested: Apple, Microsoft, Tesla, Amazon, Reliance Industries, Infosys, TCS; FY2023-2025) | MUST HAVE | None | Udhaya Kiran | 3- Completed
1 | 1 | US/102 | Prepare the 10 assigned LLM topics (LLM basics, tokens, context window, Transformer, self-attention, prompting, temperature, hallucinations, next-token prediction, LLM limitations and mitigations such as RAG, citations, structured outputs, tool calling, validation and grounding) for the Q&A session beginning 10 Sep | MUST HAVE | None | Udhaya Kiran | 3- Completed
2 | 2 | US/103 | Study financial document structures (annual reports, 10-K filings, earnings transcripts) and finalize the multi-agent architecture: orchestration flow, agent responsibilities and data models | MUST HAVE | None | Udhaya Kiran | 3- Completed
2 | 2 | US/104 | Develop the research workspace and session management: create named research sessions, manage uploaded documents and organize research work | MUST HAVE | None | Udhaya Kiran | 3- Completed
2 | 2 | US/105 | Build the Document Agent: document upload, PDF parsing, chunking, embedding generation, vector database indexing and 3-4 preloaded seed company documents | MUST HAVE | None | Udhaya Kiran | 3- Completed
2 | 2 | US/106 | Build the Extraction Agent to automatically extract financial metrics, financial ratios, revenue trends and key performance figures | MUST HAVE | None | Udhaya Kiran | 3- Completed
3 | 3 | US/107 | Build the Red Flag Agent to scan for anomalies, rising debt levels, falling margins, auditor qualifications and unusual financial patterns | MUST HAVE | None | Udhaya Kiran | 3- Completed
3 | 3 | US/108 | Implement the multi-agent orchestration layer that coordinates the Document, Extraction and Red Flag agents sequentially on document upload | MUST HAVE | None | Udhaya Kiran | 3- Completed
3 | 3 | US/109 | Test and validate agent outputs against seed financial documents for accuracy, source faithfulness and correctness | MUST HAVE | None | Udhaya Kiran | 3- Completed
3 | 3 | US/110 | Build the Research Agent to handle multi-part queries, retrieve information step by step and give reasoned answers with strict source citations | MUST HAVE | None | Udhaya Kiran | 3- Completed
3 | 3 | US/111 | Build the Comparison Agent to cross-reference extracted financial information and compare multiple company documents side by side | MUST HAVE | None | Udhaya Kiran | 3- Completed
3 | 3 | US/112 | Develop a clean chat-style conversational research interface that returns cited, reasoned answers to financial questions | MUST HAVE | None | Udhaya Kiran | 3- Completed
3 | 3 | US/113 | Begin Report Agent development: define the report structure and generate the Executive Summary and Key Financials sections | MUST HAVE | None | Udhaya Kiran | 3- Completed
4 | 4 | US/114 | Complete the Report Agent to compile agent outputs into a structured PDF report (Executive Summary, Key Financials, Red Flags, Company Comparison, Outlook) | MUST HAVE | None | Udhaya Kiran | 3- Completed
4 | 4 | US/115 | Conduct end-to-end testing: citation accuracy, agent collaboration, financial extraction correctness and report completeness | MUST HAVE | None | Udhaya Kiran | 3- Completed
4 | 4 | US/116 | Prepare a project presentation and explain Finora AI (architecture, agents and demo) in the mock assessment on 15 Oct 2026 | MUST HAVE | None | Udhaya Kiran | 3- Completed