## Defect Tracker (Comprehensive)
Sl No | Submitted By | Submitted | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Udhaya Kiran | 12-Sep-26 | PyMuPDF failed to parse non-standard document formats and header metadata during initial bulk PDF ingestion. | Sprint 1 | Udhaya Kiran | Data Validation | Implemented robust fallback text sanitization and encoding normalization in src/agents/document_agent.py to prevent page read aborts on malformed PDF streams. | 14-Sep-26 | Closed | US/101 - Discovered during initial pipeline testing on mixed PDF report batches. Fixed before vector indexing.
2 | Udhaya Kiran | 22-Sep-26 | Filename parsing corrupted document metadata. Files with non-standard naming conventions (e.g., AMAZON_ANNUAL_25.pdf or Integrated-annual-report-2025-26.pdf) resulted in empty or incorrect company and fiscal year tags. | Sprint 2 | Udhaya Kiran | Logical | Refactored _FILENAME_RE regex pattern in document_agent.py to support 2-digit years and hyphenated fiscal ranges, and added a secondary regex fallback parser to safely extract company name and 4-digit year. | 23-Sep-26 | Closed | US/105 - Found while indexing multiple reports; some documents showed wrong company/year details in their metadata.
3 | Udhaya Kiran | 24-Sep-26 | Extraction confused revenue values with EPS values. Revenue extraction regex incorrectly matched per-share figures located adjacent to total revenue tables. | Sprint 2 | Udhaya Kiran | Logical | Added strict metric classification constraints and boundary keywords in extraction_agent.py to isolate table headers and verify currency magnitudes before assigning metric values. | 25-Sep-26 | Closed | US/106 - Noticed while comparing extracted values with the annual report; the wrong figure was being picked for key financials.
4 | Udhaya Kiran | 28-Sep-26 | ChromaDB embedding batch failure during vector indexing due to chunk text exceeding max sequence length of all-MiniLM-L6-v2. | Sprint 2 | Udhaya Kiran | Functional | Adjusted CHUNK_SIZE to 800 characters and CHUNK_OVERLAP to 150 in document_agent.py, adding token truncation guards before calling sentence_transformers.encode(). | 29-Sep-26 | Closed | US/103 - Discovered during embedding generation on dense financial footnote sections in 10-K filings.
5 | Udhaya Kiran | 06-Oct-26 | Fiscal year collisions between reports. Multi-year trend analysis cross-pollinated metrics across consecutive fiscal cycles. | Sprint 3 | Udhaya Kiran | Logical | Enforced composite compound primary keys (company, year, metric_name) in ChromaDB metadata filtering and output JSON storage schema in extraction_agent.py. | 07-Oct-26 | Closed | US/106 - Reports from different years were getting mixed up, which affected trends and comparisons.
6 | Udhaya Kiran | 07-Oct-26 | Unit scaling errors in extracted financial values. Discrepancies between reports reporting in Millions, Billions, and Crores caused erratic ratio calculations. | Sprint 3 | Udhaya Kiran | Logical | Integrated unit normalization parser in extraction_agent.py that detects magnitude qualifiers ('in millions', 'in billions', '$M', '$B') and converts all figures to standardized base units. | 08-Oct-26 | Closed | US/106 - Values from different reports were on different scales (units), so comparisons looked wrong until rechecked.
7 | Udhaya Kiran | 09-Oct-26 | ZeroDivisionError in financial ratio calculation (Current Ratio and Debt-to-Equity) when balance sheets had missing or zero reported short-term liabilities. | Sprint 3 | Udhaya Kiran | Functional | Added defensive validation and null-safe ratio calculation handlers in extraction_agent.py returning None with explanatory audit remarks when denominator is zero or absent. | 10-Oct-26 | Closed | US/107 - Identified when running ratio synthesis across companies with atypical capital structures.
8 | Udhaya Kiran | 11-Oct-26 | RedFlagAgent generated duplicate risk disclosures and lacked exact page citation provenance in final summary output. | Sprint 3 | Udhaya Kiran | Data Validation | Implemented semantic deduplication using cosine similarity threshold (>0.85) and enforced mandatory provenance: {document, page_number, evidence} schema in red_flag_agent.py. | 12-Oct-26 | Closed | US/108 - Verified through automated unit tests in test_e2e_suite.py test_01_citation_accuracy.
9 | Udhaya Kiran | 15-Oct-26 | Research Copilot sometimes returns an insufficient-information message even when another part of the application (Visual Analytics) can retrieve the requested financial metric. Suspected areas: retrieval logic, metadata filtering, relevance thresholds, financial metric interpretation, differences between the Research Copilot and Visual Analytics data paths. | Sprint 4 | Udhaya Kiran | Logical | Investigated discrepancy: Visual Analytics reads pre-extracted JSON caches directly, while Research Copilot relies on semantic top-k retrieval in ChromaDB. Lowered cosine distance cutoff from 0.70 to 0.55 and added hybrid metadata-routed lookup in research_agent.py. Fix under active regression testing. | 18-Oct-26 | Open | US/110 - Noticed while preparing the project demo for the mock assessment (15 Oct); the same metric could be retrieved in Visual Analytics, so the two data paths seem to behave differently. Needs more testing before it can be closed.
10 | Udhaya Kiran | 17-Oct-26 | Automated Report Generator (ReportLab PDF) failed to render table borders and caused text overlap when metric descriptions exceeded 120 characters. | Sprint 4 | Udhaya Kiran | UI | Wrapped table cell contents in dynamic Paragraph elements with defined column widths and configured auto-wrapping Flowables in report_agent.py. | 19-Oct-26 | Closed | US/112 - Resolved layout overflow in exported executive financial summary PDFs.

## Defect Tracker (Template-5)
Sl No | Submitted By | Submitted | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Udhaya Kiran | 22-Sep-26 | Filename parsing corrupted document metadata. | Sprint 2 | Udhaya Kiran | Logical | Refactored regex pattern in document_agent.py to handle non-standard filename conventions and 2-digit years. | 23-Sep-26 | Closed | US/105 - Found while indexing multiple reports; some documents showed wrong company/year details in their metadata.
2 | Udhaya Kiran | 24-Sep-26 | Extraction confused revenue values with EPS values. | Sprint 2 | Udhaya Kiran | Logical | Updated regex boundaries and added keyword context filtering to prevent EPS figures matching total revenue. | 25-Sep-26 | Closed | US/106 - Noticed while comparing extracted values with the annual report; the wrong figure was being picked for key financials.
3 | Udhaya Kiran | 6-Oct-26 | Fiscal year collisions between reports. | Sprint 3 | Udhaya Kiran | Logical | Enforced compound primary keys (company, year, metric) in metadata and storage structure. | 7-Oct-26 | Closed | US/106 - Reports from different years were getting mixed up, which affected trends and comparisons.
4 | Udhaya Kiran | 7-Oct-26 | Unit scaling errors in extracted financial values. | Sprint 3 | Udhaya Kiran | Logical | Added unit normalization parser to detect scale qualifiers (Millions, Billions, Crores) and normalize to base figures. | 8-Oct-26 | Closed | US/106 - Values from different reports were on different scales (units), so comparisons looked wrong until rechecked.
5 | Udhaya Kiran | 15-Oct-26 | Research Copilot sometimes returns an insufficient-information message even when another part of the application (Visual Analytics) can retrieve the requested financial metric. Suspected areas: retrieval logic, metadata filtering, relevance thresholds, financial metric interpretation, differences between the Research Copilot and Visual Analytics data paths. | Sprint 4 | Udhaya Kiran | Logical | Tuned ChromaDB similarity thresholds and implemented hybrid query fallback routing between structured cache and vector search. | 18-Oct-26 | Open | US/110 - Noticed while preparing the project demo for the mock assessment (15 Oct); the same metric could be retrieved in Visual Analytics, so the two data paths seem to behave differently. Needs more testing before it can be closed.

## Defect Metrics & Summary
FINORA AI - DEFECT TRACKER METRICS
Defect Status | Count | Detected Sprint | Count
Closed Defect Count |  | Sprint 1 (Architecture & Ingestion)
Open Defect Count |  | Sprint 2 (Extraction & Vector Index)
Total Defects Logged |  | Sprint 3 (Risk & Financial Ratios)
Sprint 4 (Research Copilot & Reporting)
Project Details | Value
Project Name | Finora AI — Multi-Agent Financial Intelligence
Intern / Engineer Name | Udhaya Kiran
Role | AI Engineering & Multi-Agent Development Intern
Organization / Platform | Infosys Internship