## Unit Test Cases (UTP)
FINORA AI — UNIT TEST PLAN & EXECUTION SPECIFICATION
Project: Multi-Agent Financial Analysis System ¦ Tester: Udhaya Kiran ¦ Platform: Infosys Internship
Test Case ID | Module Name | User Story ID | Test Scenario / Objective | Preconditions & Test Data | Test Execution Steps | Expected Result | Actual Result | Status | Tested By | Execution Date | Linked Defect / Notes
UTC_001 | Document Agent | US/101 | Verify PyMuPDF text extraction across multi-page annual report PDFs. | DATA/AMAZON_ANNUAL_2023.pdf exists in directory; PyMuPDF installed. | 1. Instantiate DocumentAgent. 2. Call extract_pages_to_json('DATA/AMAZON_ANNUAL_2023.pdf'). 3. Verify page count and extracted text length. | Structured JSON containing all pages with non-empty text blocks saved to processed/json/. | All pages extracted cleanly with preserved page numbering. JSON artifact verified. | Pass | Udhaya Kiran | 14-Sep-26 | Initial ingestion pipeline validated.
UTC_002 | Document Agent | US/105 | Verify filename parsing for irregular naming conventions and 2-digit years. | PDFs: AMAZON_ANNUAL_25.pdf, Integrated-annual-report-2025-26.pdf. | 1. Pass varying filenames to DocumentAgent._parse_filename(). 2. Inspect extracted (company, year) tuple. | Properly parsed ('AMAZON', '2025') and company/year metadata tags without corruption. | Correctly extracted 4-digit years and normalized company names without raising parsing exceptions. | Pass | Udhaya Kiran | 23-Sep-26 | Linked to Defect #1 - Regex updated & verified.
UTC_003 | Document Agent | US/102 | Verify text chunking and overlap consistency for vector embeddings. | Extracted JSON document from processed/json/. | 1. Execute chunking with CHUNK_SIZE=800, OVERLAP=150. 2. Validate chunk character boundaries and sequential IDs. | All chunks strictly <= 800 chars with continuous 150-char sliding overlap and valid chunk_id. | Chunk bounds preserved, metadata attributes (doc_name, page_number) correctly attached. | Pass | Udhaya Kiran | 25-Sep-26 | Chunks saved to processed/chunks/ correctly.
UTC_004 | ChromaDB Manager | US/103 | Verify embedding generation and persistent vector indexing in ChromaDB. | Generated chunk files in processed/chunks/; sentence-transformers all-MiniLM-L6-v2 loaded. | 1. Run ChromaManager.add_chunks(). 2. Query collection count and query top-k by cosine similarity. | Embeddings successfully inserted into ChromaDB without token truncation errors; similarity search returns relevant chunks. | Embeddings generated in batches of 64; persistent collection verified with zero dimension errors. | Pass | Udhaya Kiran | 29-Sep-26 | Token length truncation guard validated.
UTC_005 | Extraction Agent | US/106 | Verify revenue extraction distinction from per-share EPS values. | APPLE 2024 indexed ChromaDB collection. | 1. Run ExtractionAgent.extract('APPLE', '2024'). 2. Inspect revenue and net_income parsed values against source 10-K. | Revenue correctly captured as multi-billion dollar total figure, not confused with adjacent EPS decimals. | Revenue = $391,035M accurately captured; distinct from EPS ($6.08). Verified against 10-K. | Pass | Udhaya Kiran | 25-Sep-26 | Linked to Defect #2 - Header context regex verified.
UTC_006 | Extraction Agent | US/106 | Verify unit scaling and normalization across diverse reporting magnitudes. | Reports with mixed units: Millions ($M), Billions ($B), and Crores (INR). | 1. Trigger extraction across AMAZON (Millions) and INFOSYS (Crores). 2. Verify base numerical normalization. | All metrics transformed into standard numeric values (float/int) with scaling multiplier applied. | Magnitude qualifiers successfully parsed and converted to uniform base values. | Pass | Udhaya Kiran | 08-Oct-26 | Linked to Defect #4 - Unit scaling verified.
UTC_007 | Extraction Agent | US/107 | Verify derived financial ratio consistency and zero-division defensive guards. | Extracted metrics for APPLE 2024 (Revenue, Net Income, Assets, Liabilities). | 1. Calculate Net Profit Margin, ROA, Debt-to-Equity. 2. Pass zero denominator to test guard. | Net Profit Margin matches (Net Income / Revenue) within 2 decimals; zero denominator returns None safely. | Net Profit Margin formula verified: net_margin == net_income / revenue. Defensive None returned for zero divisor. | Pass | Udhaya Kiran | 10-Oct-26 | Verified in test_02_extraction_correctness.
UTC_008 | Red Flag Agent | US/108 | Verify risk disclosure detection and citation provenance schema. | AMAZON 2023 indexed document chunks in ChromaDB. | 1. Run RedFlagAgent.scan('AMAZON', '2023'). 2. Inspect returned red_flags list and provenance keys. | Identifies valid operational/financial risk disclosures; each flag includes document, page_number, and evidence quote. | Verified red flag citations with textual evidence and valid page references. Zero hallucinated citations. | Pass | Udhaya Kiran | 12-Oct-26 | Verified in test_01_citation_accuracy.
UTC_009 | Comparison Agent | US/106 | Verify multi-year and multi-company benchmark comparison without fiscal collisions. | TESLA (2023, 2024) and APPLE (2024) extracted metric sets. | 1. Run ComparisonAgent.compare([('TESLA','2023'), ('TESLA','2024'), ('APPLE','2024')]). 2. Check year separation. | Comparison matrix preserves distinct annual columns with zero cross-pollination of fiscal metrics. | Compound keys (company, year, metric) cleanly isolated metrics; trend deltas computed accurately. | Pass | Udhaya Kiran | 07-Oct-26 | Linked to Defect #3 - Fiscal collisions eliminated.
UTC_010 | LangGraph Pipeline | US/109 | Validate 4-stage end-to-end multi-agent orchestration (Doc -> Ext -> RedFlag -> Report). | Valid PDF: TESLA_ANNUAL_2023.pdf. | 1. Execute OrchestrationPipeline.run_for_doc_id('TESLA', '2023'). 2. Validate FinancialState data flow across all nodes. | All 4 agents execute sequentially, populating FinancialState without data drop or pipeline stall. | Pipeline completed execution; doc_id, extraction, red_flags, and report artifacts confirmed on disk. | Pass | Udhaya Kiran | 14-Oct-26 | Verified in test_03_agent_collaboration.
UTC_011 | Report Agent | US/112 | Verify automated ReportLab executive PDF generation with 5 mandatory sections. | Extracted metrics, red flag summary, and comparison matrix for META 2024. | 1. Run ReportAgent.generate('META', '2024', ...). 2. Inspect generated PDF, JSON, and Markdown files. | Generates PDF (>1KB) with 5 structured sections: Exec Summary, Key Financials, Red Flags, Comparison, and Outlook. | All 5 sections confirmed; valid PDF generated (>1000 bytes) with cleanly wrapped table cells. | Pass | Udhaya Kiran | 19-Oct-26 | Verified in test_04_report_completeness.
UTC_012 | Research Copilot | US/110 | Validate Research Copilot RAG query response and grounding against financial metrics. | ChromaDB indexed documents + query: 'What are Amazon revenue drivers and risks in 2023?'. | 1. Send query to ResearchAgent.query(). 2. Compare retrieved context against Visual Analytics cache. | Returns factual, source-grounded response with specific dollar amounts and page citations without generic refusal. | Hybrid retrieval fallback implemented; queries now cross-reference pre-extracted metrics and semantic vector chunks. | Pass | Udhaya Kiran | 18-Oct-26 | Linked to Defect #5 - Hybrid lookup validated.

## Defect Tracker & Resolutions
FINORA AI — SPRINT DEFECT TRACKER & RESOLUTION LOG
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Udhaya Kiran | 22-Sep-26 | Filename parsing corrupted document metadata. | Sprint 2 | Udhaya Kiran | Logical | Refactored regex pattern in document_agent.py to support non-standard naming conventions and 2-digit years; added secondary fallback parser for company/year metadata. | 23-Sep-26 | Closed | US/105 - Found while indexing multiple reports; some documents showed wrong company/year details in their metadata.
2 | Udhaya Kiran | 24-Sep-26 | Extraction confused revenue values with EPS values. | Sprint 2 | Udhaya Kiran | Logical | Updated regex boundaries and added keyword context filtering to prevent EPS per-share figures matching total gross revenue. | 25-Sep-26 | Closed | US/106 - Noticed while comparing extracted values with the annual report; the wrong figure was being picked for key financials.
3 | Udhaya Kiran | 6-Oct-26 | Fiscal year collisions between reports. | Sprint 3 | Udhaya Kiran | Logical | Enforced compound primary keys (company, year, metric) in metadata filtering and JSON storage to guarantee annual isolation. | 7-Oct-26 | Closed | US/106 - Reports from different years were getting mixed up, which affected trends and comparisons.
4 | Udhaya Kiran | 7-Oct-26 | Unit scaling errors in extracted financial values. | Sprint 3 | Udhaya Kiran | Logical | Added unit normalization parser to detect scale qualifiers (Millions, Billions, Crores) and normalize to base numeric figures. | 8-Oct-26 | Closed | US/106 - Values from different reports were on different scales (units), so comparisons looked wrong until rechecked.
5 | Udhaya Kiran | 15-Oct-26 | Research Copilot sometimes returns an insufficient-information message even when another part of the application (Visual Analytics) can retrieve the requested financial metric. Suspected areas: retrieval logic, metadata filtering, relevance thresholds, financial metric interpretation, differences between the Research Copilot and Visual Analytics data paths. | Sprint 4 | Udhaya Kiran | Logical | Tuned ChromaDB similarity distance thresholds and implemented hybrid query fallback routing between structured pre-extracted JSON caches and semantic vector search. | 18-Oct-26 | Closed | US/110 - Noticed while preparing the project demo for the mock assessment (15 Oct); the same metric could be retrieved in Visual Analytics. Re-tested and verified.

## Test Execution Summary
FINORA AI — UNIT TEST EXECUTION DASHBOARD
Test Execution Metric | Value | Subsystem / Module | Test Coverage
Total Unit Test Cases Planned |  | Document Agent & PyMuPDF Ingestion | 100% Passed (UTC_001, UTC_002, UTC_003)
Total Test Cases Executed |  | ChromaDB Vector Store & Embeddings | 100% Passed (UTC_004)
Total Tests Passed |  | Extraction Agent & Ratio Synthesizer | 100% Passed (UTC_005, UTC_006, UTC_007)
Total Tests Failed |  | Red Flag Disclosure & Citation Agent | 100% Passed (UTC_008)
Unit Test Pass Rate | 100.0% | Comparison Agent Benchmarking | 100% Passed (UTC_009)
Defects Detected & Resolved | 5 / 5 Closed | LangGraph Multi-Agent Orchestrator | 100% Passed (UTC_010)
|  | ReportLab Executive PDF Generator | 100% Passed (UTC_011)
|  | Research Copilot Hybrid Query RAG | 100% Passed (UTC_012)
Sign-off & Approval | Details
Student / Intern Name | Udhaya Kiran
Role | AI Engineering & Multi-Agent Intern
Testing Scope | Unit Testing, Integration Testing, Defect Resolution
Evaluation Milestone | Milestone Assessment / Final Project Review
Test Completion Status | COMPLETED & VERIFIED (All tests passed)